## Sheet1
Module (For Hare Love) |  |  |  | Estimate |  | Actual |  | Comments
Name | ID | Depends | Resource | Start Week | End Week | Start Week | End Week | Based on weeks because these tasks overlapped during each week
Game Idea Creation | 1 |  | Ed | 1 | 1 | 1 | 1
Research | 2 | 1 | Google | 2 | 2 | 2 | 2
Level Designs | 3 | 2 | Ed | 3 | 3 | 3 | 3
Placing basic Unity assets | 4 | 3 | Unity | 4 | 4 | 4 | 4
Programming Multi-Cube | 5 |  | Unity script referecence and Google | 5 | 5 | 5 | 6
Programming Health Bar | 6 |  | Unity script referecence and Google | 6 | 6 | 6 | 10 | Needed help from Paul and Unity guide on Charcter Collider stuff
Programming GUI and Health Bar | 7 | 6 | Unity script referecence and Google | 6 | 6 | 6 | 10 | "
Programming Damage | 8 | 6 | Paul | 9 | 9 | 9 | 10
Programming Add Health | 9 | 8 | Paul and Jakub | 10 | 11 | 10 | 10
Menu | 10 |  | Ed and previous Unity game | 11 | 11 | 11 | 11 | Menu script I used in game from last semester